## MEESHO WEBSITE SCENARIOS
| Project Name: | MEESHO
| Module Name: | MEESHO WEBSITE
| Created By: | NIKHIL TEVANI
| Date of Creation: | 2026-03-05
| Date of Review: | NEED TO REVIEW
Test Case ID | Requirement Id | Test Case Scenario | Test Case Description | Precondition | Test case steps Taken | Test Data | Expected Result | Actual Result | Status | Defect ID
TC01 | R-101 | Validating if user can navigate to the footer section on Home page | Verify that user is able to navigate to the footer section without interruption | 1. User must be logged in to Meesho Application 2. User must be on homepage | 1. Open the Meesho application and log in with Userid and Password 2. Navigate to the Home Page 3. Scroll down the page till bottom 4. Observe the loading behavior of page elements | UserID - Meesho_User Password - User12345 | User should be able to reach the footer section without any interruption | Unable to reach the footer section because page elements keep loading continuously | FAILED | Defect_ID_01
TC02 | R-102 | Validating display message when user searches for any product | Verify that clarification message should be displayed when corrected search results are shown | 1. User must be logged in to Meesho Application 2. User must be on homepage | 1. Open the Meesho application and log in with Userid and Password 2. Navigate to the Home Page 3. Click on Search bar and search for "hello Bag" 4. Enter Search | UserID - Meesho_User Password - User12345 | User should be able to see message "Showing results for yellow bag" if the search result is not displayed for "hello bag" | Unable to see "Showing results for yellow bag" message upon searching "hello bag" | FAILED | Defect_ID_02
TC03 | R-103 | Validating if Pet Supplies category image is displaying on home page | Veify if all categories images are displaying including Pet Supplies category on home page | 1. User must be logged in to Meesho Application 2. User must be on homepage | 1. Open the Meesho application and log in with Userid and Password 2. Navigate to the Home Page 3. Check for categories present on home page 4. Check the category image for "Pet Supplies" | UserID - Meesho_User Password - User12345 | User should be able to see Pet Category Image on home page once login | No Pet Category Image displayed on home page | FAILED | Defect_ID_03
TC04 | R-104 | Validating page navigation and consistency when user clicks on "Become a Supplier" tab | Verify that page elements are present and page is synchronized with rest of the web application (header/footer inconsistency) when user clicks on "Become a Supplier" in the top header | 1. User must be logged in to Meesho Application 2. User must be on homepage 3. User must be able to click on "Become a Supplier" tab in the top header | 1. Open the Meesho application and log in with Userid and Password 2. Navigate to the Home Page 3. Check for "Become a Supplier" tab in the top header and click on it 4. Check for back button once clicked on "Become a Supplier" tab 5. Check if page layout is in sync with the rest of the web application (header/footer inconsistency) | UserID - Meesho_User Password - User12345 | User should be able to see back button and validate the page is in sync with with the rest of the web application (header/footer inconsistency) once click on "Become a Supplier" tab | Back button is not present and page is not in sync with rest of the web application on clicking "Become a Supplier" tab | FAILED | Defect_ID_04
TC05 | R-105 | Validating Delete Account option is hidden when account is not logged in | Verify that there should not be Delete Account option present on web application when user is not logged into account | 1. User must be logged in to Meesho Application 2. User must be on homepage 3. User must not logged into account | 1. Open the Meesho application 2. Hover on Profile icon on the right top corner | UserID - Meesho_User Password - User12345 | User should not be able to see Delete Account option if not logged in to the web application | Delete Account option present on web application even if user is not logged in | FAILED | Defect_ID_05